## Rev. 2-8-2023
SP&R-2 ACTIVITIES TIMELINE (Critical Path and concurrent) (2/15/2023)
Milestone A | Establish Research Needs | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | ~ RSC Q MTG Month
1 | Oklahoma Transportation Research Day (OTRD) | OCT: 15th; NOV: <<<<<<<<<<<<<<<<< OTRD Planning Meetings >>>>>>>>>>>>>>>>
2 | External/Internal Research Topics Solicitation (Problem Statements, Innovations Discovered, Research Ideas, Res. Continuance Requests) | NOV: 30th
3 | Categorization and Combination of Research Topics Received | DEC: 20th
4 | Distribution, Review and Ratings of Topic Statements by Subject Matter Experts (SMEs) | JAN: 31st
5 | Research Programs to Discuss SME Rated Research Topics, Submit Recommended Shortlist to Deputy Chief Innovation Officer. Receive Direction and Revise. | FEB: 15th
6 | Estimate # of Projects Ending + # of Possible New Projects for Upcoming FFY > Request From SPR Program Manager an Estimate of Funds available for Next SPR Part 2 FFYRequest From SPR Program Manager an Estimate of Funds available for Next SPR Part 2 FFY | FEB: 15th
7 | Distribute Revised Short List of Next FFY Topic Statements to RSC | FEB: by the 21st
8a | Present to Research Steering Committee (RSC) at 1st Quarter Meeting | FEB: by the 28th
8b | ODOT RSC Selection of Topics to Move Forward / Discuss ODOT Champion and Subject Matter Expert for Each Topic Selected Based on Potential Need, Timeliness, Implementation & Benefits | FEB: by the 28th
9 | Prepare RSC's List of Projects to be Funded (Priority: #1 General, #2 Continuing SPR, #3 Continuing TPF, #4 New SPR and New TPF) | MAR: 15th
10 | Request/ Receive Deputy Chief Innovation Officer Approval of Continuing and New Research Recommended for Funding | MAR: 20th
11 | New RFP Literature and Database Searches (TRIS, RIP, Pooled Fund Studies,...) | MAR: 25th
12 | Prepare Each RFP, Review by SME/ Spomsor, and Post Approved RFPs; Notify Contractors (Links/ Submission Forms & Guidelines) | MAR: 31st
13 | Assign / Document ODOT Champion (Division/ District Sponsor, Subject Matter Expert, RPM Project Manager) | MAR: 31st
Milestone B | Selection and Approval of Proposals | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | ~ RSC Q MTG Month
1 | Proposals Submitted w/Letter of Support from Division or District | 31st APR: 30th
2 | Distribution of Proposals to ODOT Subject Matter Experts | 31st MAY: 10th
3 | ODOT Sponsor/ SME Review and Selection from Proposals Submitted | 31st MAY: 20th
4 | Research Steering Committee (RSC) at 2nd Quarter Meeting | 31st MAY: by the 31st
5 | Obtain Commitment of Division Resources (Sponsorship Form) | 31st JUN: 10th
6 | PI Proposal Negotiations & Revisions (if any) | 31st JUN: 30th
7 | Approval of Revisions from Subject Matter Expert(s) | 31st JUL: 10th
8 | Receive Deputy Chief Innovation Officer Approval to Fund Project and Include in Next SPR Work Prpogram | 31st JUL: 20th
Milestone C | Federal Highway Administration Approval | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | ~ RSC Q MTG Month
1 | Federal SP&R Part 2 Work Plan Preparation | 20th JUL: 20th
2 | Submission of SP&R Work Plan for FHWA Concurrence | 20th JUL: 31st
3 | Federal SP&R Work Plan Approval | 20th AUG: 30th
| Research Steering Committee (RSC) at 3rd Quarter Meeting | 20th AUG: by the 31st
4 | Annual Performance & Expenditures Report | JAN: 10th
Milestone D | Execution of Contracts | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | ~ RSC Q MTG Month
1 | Prepare Annual, Continuing and New Contracts w/Proposal attached; No Cost Extensions (NCE) | 10th JUL: 30th
2 | Transmittal to Contractor for Partial Contract Execution | 10th SEP: 15th
3 | Route for ODOT Full Contract Execution | 10th SEP: 20th
4 | Transmittal of Approved Contract Package to Contractor | 10th SEP: 30th
Milestone E | Project Administration | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | ~ RSC Q MTG Month
1 | Research In Progress (RIP) Entries & Removals | OCT: 31st
2 | Research Steering Committee (RSC) at 4th Quarter Meeting | NOV: by the 31st
3 | Project Initiation Meeting - w/Project Panel Members, PI and Assigned RPM | NOV: 10th
4 | Invoices w/Progress Reports Processing (Compliance / % complete) |  | 15th | 15th | 15th | 15th | 15th | 15th | 15th | 15th | 15th | 15th | 15th
5 | Annual Project Status / Draft Final Reports Submittal for previous FFY | OCT: 31st
6 | Engineering, Document Formatting & ADA Review of Annual, Draft Final or Final Reports | NOV: 30th
7 | Project Panel Member Review and Comments for Report Revisions | NOV: 30th
8 | Distribution of Final Report w/Revisions | DEC: 20th