## Current
|  | 2010 |  |  |  | 2011 | [11 empty] | 2012 | [11 empty] | 2013 | [11 empty] | 2014 | [11 empty] | 2015 | [11 empty] | 2016 | [11 empty] | 2017 | [11 empty] | 2018 | [11 empty] | 2019 | [11 empty] | 2020 | [11 empty] | 2021 | [11 empty] | 2022
| DATE | SEPTEMBER | OCTOBER | NOVEMBER | DECEMBER | JANUARY | FEBRUARY | MARCH | APRIL | MAY | JUNE | JULY | AUGUST | SEPTEMBER | OCTOBER | NOVEMBER | DECEMBER | JANUARY | FEBRUARY | MARCH | APRIL | MAY | JUNE | JULY | AUGUST | SEPTEMBER | OCTOBER | NOVEMBER | DECEMBER | JANUARY | FEBRUARY | MARCH | APRIL | MAY | JUNE | JULY | AUGUST | SEPTEMBER | OCTOBER | NOVEMBER | DECEMBER | JANUARY | FEBRUARY | MARCH | APRIL | MAY | JUNE | JULY | AUGUST | SEPTEMBER | OCTOBER | NOVEMBER | DECEMBER | JANUARY | FEBRUARY | MARCH | APRIL | MAY | JUNE | JULY | AUGUST | SEPTEMBER | OCTOBER | NOVEMBER | DECEMBER | JANUARY | FEBRUARY | MARCH | APRIL | MAY | JUNE | JULY | AUGUST | SEPTEMBER | OCTOBER | NOVEMBER | DECEMBER | JANUARY | FEBRUARY | MARCH | APRIL | MAY | JUNE | JULY | AUGUST | SEPTEMBER | OCTOBER | NOVEMBER | DECEMBER | JANUARY | FEBRUARY | MARCH | APRIL | MAY | JUNE | JULY | AUGUST | SEPTEMBER | OCTOBER | NOVEMBER | DECEMBER | JANUARY | FEBRUARY | MARCH | APRIL | MAY | JUNE | JULY | AUGUST | SEPTEMBER | OCTOBER | NOVEMBER | DECEMBER | JANUARY | FEBRUARY | MARCH | APRIL | MAY | JUNE | JULY | AUGUST | SEPTEMBER | OCTOBER | NOVEMBER | DECEMBER | JANUARY | FEBRUARY | MARCH | APRIL | MAY | JUNE | JULY | AUGUST | SEPTEMBER | OCTOBER | NOVEMBER | DECEMBER | JANUARY | FEBRUARY | MARCH | APRIL | MAY | JUNE | JULY | AUGUST | SEPTEMBER | OCTOBER | NOVEMBER | DECEMBER
JP 21006(04) - TETRA TECH: BRIDGES 13079, 10053
Initiation | 2010-09-01 | bar: 2010 SEPTEMBER
Survey | 2015-03-21 | bar: 2015 MARCH
Hydraulics | 2015-04-23 | bar: 2015 APRIL
30% | 2015-06-04 | bar: 2015 JUNE
R/W 60% | 2015-06-04 | bar: 2015 JUNE
R/W Submit | 2015-06-29 | bar: 2015 JUNE
NEPA Clearance | 2017-09-20 | bar: 2017 SEPTEMBER
90% | 2017-05-25 | bar: 2017 MAY
PSE Target | 2019-03-15 | bar: 2019 MARCH
R/W - UT Target | 2019-11-16 | bar: 2019 NOVEMBER
JP 21006(11) - TETRA TECH: BRIDGES 13653,13925
Initiation | 2010-09-01 | bar: 2010 SEPTEMBER
Survey | 2015-03-21 | bar: 2015 MARCH
Hydraulics | 2015-04-23 | bar: 2015 APRIL
30% | 2015-06-04 | bar: 2015 JUNE
R/W 60% | 2015-06-04 | bar: 2015 JUNE
R/W Submit | 2015-06-29 | bar: 2015 JUNE
NEPA Clearance | 2017-09-20 | bar: 2017 SEPTEMBER
90% | 2017-05-25 | bar: 2017 MAY
PSE Target | 2019-03-15 | bar: 2019 MARCH
R/W - UT Target | 2019-11-16 | bar: 2019 NOVEMBER
JP 21006(07) - CPYI: BRIDGES ?, ?
Initiation | 2010-09-01 | bar: 2010 SEPTEMBER
Survey | 2015-03-21 | bar: 2015 MARCH
Hydraulics | 2015-03-28 | bar: 2015 MARCH
30% | 2015-04-08 | bar: 2015 APRIL
R/W 60% | 2015-04-08 | bar: 2015 APRIL
R/W Submit | 2015-07-16 | bar: 2015 JULY
NEPA Clearance | 2017-09-09 | bar: 2017 SEPTEMBER
90% | 2017-02-14 | bar: 2017 FEBRUARY
PSE Target | 2018-10-01 | bar: 2018 OCTOBER
R/W - UT Target | 2019-06-19 | bar: 2019 JUNE
US-270 BUNDLE PROJECT
Review Environmental | bar: 2019 JANUARY
R/W Acquisition Begins | bar: 2019 JANUARY
Final PSE Plans received from CP&Y | bar: 2019 JANUARY
Final PSE Plans received from Tetra Tech | bar: 2019 MARCH
Final PSE Plans received from Tetra Tech & CP&Y (Bundle) | bar: 2019 MARCH
Begin Utility relocation | bar: 2019 JULY
Let through competitive bid | bar: 2020 JUNE
Complete Construction | bar: 2022 OCTOBER

## Bundled
|  | 2010 |  |  |  | 2011 | [11 empty] | 2012 | [11 empty] | 2013 | [11 empty] | 2014 | [11 empty] | 2015 | [11 empty] | 2016 | [11 empty] | 2017 | [11 empty] | 2018 | [11 empty] | 2019 | [11 empty] | 2020 | [11 empty] | 2021 | [11 empty] | 2022
| DATE | SEPTEMBER | OCTOBER | NOVEMBER | DECEMBER | JANUARY | FEBRUARY | MARCH | APRIL | MAY | JUNE | JULY | AUGUST | SEPTEMBER | OCTOBER | NOVEMBER | DECEMBER | JANUARY | FEBRUARY | MARCH | APRIL | MAY | JUNE | JULY | AUGUST | SEPTEMBER | OCTOBER | NOVEMBER | DECEMBER | JANUARY | FEBRUARY | MARCH | APRIL | MAY | JUNE | JULY | AUGUST | SEPTEMBER | OCTOBER | NOVEMBER | DECEMBER | JANUARY | FEBRUARY | MARCH | APRIL | MAY | JUNE | JULY | AUGUST | SEPTEMBER | OCTOBER | NOVEMBER | DECEMBER | JANUARY | FEBRUARY | MARCH | APRIL | MAY | JUNE | JULY | AUGUST | SEPTEMBER | OCTOBER | NOVEMBER | DECEMBER | JANUARY | FEBRUARY | MARCH | APRIL | MAY | JUNE | JULY | AUGUST | SEPTEMBER | OCTOBER | NOVEMBER | DECEMBER | JANUARY | FEBRUARY | MARCH | APRIL | MAY | JUNE | JULY | AUGUST | SEPTEMBER | OCTOBER | NOVEMBER | DECEMBER | JANUARY | FEBRUARY | MARCH | APRIL | MAY | JUNE | JULY | AUGUST | SEPTEMBER | OCTOBER | NOVEMBER | DECEMBER | JANUARY | FEBRUARY | MARCH | APRIL | MAY | JUNE | JULY | AUGUST | SEPTEMBER | OCTOBER | NOVEMBER | DECEMBER | JANUARY | FEBRUARY | MARCH | APRIL | MAY | JUNE | JULY | AUGUST | SEPTEMBER | OCTOBER | NOVEMBER | DECEMBER | JANUARY | FEBRUARY | MARCH | APRIL | MAY | JUNE | JULY | AUGUST | SEPTEMBER | OCTOBER | NOVEMBER | DECEMBER | JANUARY | FEBRUARY | MARCH | APRIL | MAY | JUNE | JULY | AUGUST | SEPTEMBER | OCTOBER | NOVEMBER | DECEMBER
JP 21006(04) - TETRA TECH: BRIDGES 13079, 10053
Initiation | bar: 2010 SEPTEMBER
Survey | bar: 2015 MARCH
Hydraulics | bar: 2015 APRIL
30% | bar: 2015 JUNE
R/W 60% | bar: 2015 JUNE
R/W Submit | bar: 2015 JUNE
NEPA Clearance | bar: 2017 SEPTEMBER
90% | bar: 2017 MAY
PSE Target
R/W - UT Target
JP 21006(11) - TETRA TECH: BRIDGES 13653,13925
Initiation | bar: 2010 SEPTEMBER
Survey | bar: 2015 MARCH
Hydraulics | bar: 2015 APRIL
30% | bar: 2015 JUNE
R/W 60% | bar: 2015 JUNE
R/W Submit | bar: 2015 JUNE
NEPA Clearance | bar: 2017 SEPTEMBER
90% | bar: 2017 MAY
PSE Target
R/W - UT Target
JP 21006(07) - CPYI: BRIDGES ?, ?
Initiation | bar: 2010 SEPTEMBER
Survey | bar: 2015 MARCH
Hydraulics | bar: 2015 MARCH
30% | bar: 2015 APRIL
R/W 60% | bar: 2015 APRIL
R/W Submit | bar: 2015 JULY
NEPA Clearance | bar: 2017 SEPTEMBER
90% | bar: 2017 FEBRUARY
PSE Target
R/W - UT Target
US-270 BUNDLE PROJECT
Review Environmental | 2019-01-01
R/W Acquisition Begins | 2019-01-01
Final PSE Plans received from CP&Y | 2019-01-01
Final PSE Plans received from Tetra Tech | 2019-03-01
Final PSE Plans received from Tetra Tech & CP&Y (Bundle) | 2019-03-01
Begin Utility relocation | 2019-07-01
Let through competitive bid | 2020-06-01
Construct Bridges | 2022-10-01
Complete Construction | 2022-10-01